## Sheet1
Duration
Phase 1: Define Objectives and Plan | 1 Week
Step 1: Define Scope
Clearly state the project's purpose:
Recommend travel destinations based on users’ past travel experiences.
Build a travel log feature for users to record and analyze their journeys.
Step 2: Gather Resources
Skills: Python, machine learning basics, data handling, and web development.
Tools:
Python libraries: pandas, numpy, scikit-learn, spaCy/NLTK.
API familiarity: Google Maps, TripAdvisor, or similar.
Frontend: Streamlit (for simplicity) or ReactJS.
Step 3: Identify Data Sources
Use publicly available travel datasets or APIs:
Kaggle: Look for travel-related datasets.
APIs: Google Places, TripAdvisor, Yelp for real-time data.
Scraping (if allowed): Collect metadata from travel blogs.
Phase 2: Build the Foundation | 2 Weeks
Step 4: Set Up Development Environment
1. Install Necessary Tools:
Install Python and IDE (VSCode, PyCharm, or Jupyter Notebook).
Install libraries: pip install pandas numpy scikit-learn spaCy streamlit.
2. Organize Your Project Directory:
bash
Copy code
travel-recommendation/
├── data/ # For raw and processed data
├── src/ # For code modules
├── notebooks/ # For prototyping
├── app/ # For the web app interface
└── README.md # Documentation
Step 5: Create a Travel Log System
Design a schema for storing user travel experiences:
Use a simple structure like CSV, SQLite, or NoSQL (MongoDB).
Example Schema:
json
Copy code
{
"user_id": "123",
"destination": "Switzerland",
"activity": "skiing",
"environment": "snowy mountains",
"rating": 5,
"notes": "Loved the views."
}
Develop a form or interface for users to input their experiences.
Phase 3: Build the Recommendation System | 3-4 Weeks
Step 6: Process Data
Travel Data Preparation:
Collect or simulate sample travel experiences and destination data.
Clean and preprocess data using pandas.
Standardize attributes (e.g., activity types, emotions).
Step 7: Implement NLP for Experience Matching
1. Text Preprocessing:
Tokenize user input.
Extract key components (activity, emotion, environment) using spaCy or NLTK.
2. Match Similar Experiences:
Use TF-IDF or word embeddings (e.g., Word2Vec or BERT) to compute similarity.
Create a basic recommendation algorithm:
python
Copy code
from sklearn.metrics.pairwise import cosine_similarity
# Example similarity function
def recommend_experience(user_input, destination_data):
similarity = cosine_similarity(user_input, destination_data)
return sorted(similarity, reverse=True)[:5]
Step 8: Build a Recommendation Model
Start simple with a content-based filtering model:
Match user preferences with destination metadata.
Add enhancements like collaborative filtering or hybrid approaches later.
Phase 4: Create a User Interface | 2 Weeks
Step 9: Develop a Web App
1. Use Streamlit for a simple frontend:
Display user travel logs.
Show interactive recommendations.
2. Add visualizations:
Use Google Maps API to display destinations on a map.
Show graphs for travel history and preferences.
Step 10: Implement User Interaction
Allow users to:
Add experiences to their travel log.
View recommended destinations with details (activities, reviews, photos).
Filter by budget, season, or travel distance.
Phase 5: Test and Iterate | 1-2 Weeks
Step 11: Test Your System
Create test cases for the recommendation engine.
Collect feedback from users to refine:
Are recommendations accurate?
Is the UI intuitive?
Step 12: Deploy and Share
Deploy your app:
Use Heroku, AWS, or Streamlit Cloud for hosting.
Share with friends or on GitHub for feedback.
Phase 6: Enhance the System | Ongoing
Step 13: Add Advanced Features
Dynamic Recommendations: Incorporate real-time data like weather, events, or local trends.
Social Integration: Allow users to share travel logs and recommendations with others.
Machine Learning Models:
Train a deep learning model for experience classification or advanced similarity matching.
Step 14: Market Your Project
Document your project on GitHub with a clear README.
Showcase it on your portfolio and LinkedIn.
Highlight its potential for future applications in your job applications.